Prepared for: 								Prepared by:

CoIPR Team								Aascent InfoSolutions

Contents:

Contents

1. Introduction	2

1.1 Purpose of this Proposal	3

1.2 About Aascent InfoSolutions	3

1.3 Executive Summary	3

1.4 Objectives	4

1.5 What We Are Building & Why	4

2. Scope of Work	4

2.1 Project Scope Overview	5

2.2 In-Scope Functional Components	5

1. User Authentication & Security	6

2. Integration with EHR System	6

3. Patient Data Management	6

4. Rule-Based Decision Engine (Core MVP)	6

5. Rounding List Generation	6

6. Decision Explanation & Compliance Visibility	7

7. User Interface (Web Application)	7

8. Audit & Logging	7

User activity tracking	7

9. Deployment & Hosting	7

2.3 Out of Scope (Version 1)	7

2.4 Deliverables	8

3. System Requirements Specifications	8

3.1 Stakeholders	8

4. Solution Overview	8

4.1 Overall Approach	8

4.2 Key Features	8

Core (MVP)	9

Advanced	9

AI (Future)	9

5.0. Phase-wise Implementation Plan	9

5.1   Phase-0 | PCC Workflow Review — Technical Contribution	9

5.1.1 Phase 0 Integration Data Flow Diagram	9

5.1.2 Phase 0 — Feature / Task Breakdown	10

5.1.3 Phase 0 — Effort Summary by Role	11

5.1.4 Phase 0 — Cost & Timeline	12

5.2 PHASE 1   |   Sandbox Validation & Logic Engine Prototype	12

5.2.1 Logic Engine Prototype Flow Diagram	12

5.2.2 Phase 1 Deliverables (Locked)	13

5.2.3 Phase 1 — Feature / Task Breakdown	13

5.2.4 Phase 1 — Effort Summary by Role	14

5.2.5 Phase 1 — Cost & Timeline	14

5.3 PHASE 2   |   Build, Test & Deploy — Production V1	15

5.3.1 System Architecture Diagram	15

5.3.2 Phase 2 Deliverables (Locked)	15

5.3.3 Phase 2 — Feature / Task Breakdown	16

5.3.4 Phase 2 — Effort Summary by Role	19

5.3.5 Phase 2 — Cost & Timeline	20

6.0 Sample UI Screens	20

6.1. Login Screen	20

6.2. Rounding List Screen	21

6.3. Admin Rule Management	22

6.4 Why our team is a fit	23

6.5 Proposed Technology Stack	24

6.6 Questions & Assumptions	24

7.0. Team Structure	25

8. Aascent Confirmations	25

8.1 GCP Capability	25

8.2 HIPAA BAA	26

8.3 Backend Framework	26

8.4 Phase Timeline Trigger	26

8.5 PM Model	26

9. Agreement Terms	26

10. Acceptance	27

# 1. Introduction

### 1.1 Purpose of this Proposal

- The purpose of this document is to define the vision, architecture, and implementation approach for developing a Smart Rounding & Compliance Platform for post-acute and long-term care facilities.

- The system aims to:

  - Automate patient selection for provider rounding

  - Reduce manual chart review effort

  - Ensure compliance with regulatory requirements

  - Provide explainable decision support for clinicians

  - Establish a scalable foundation for AI-driven healthcare insights

## 1.2 About Aascent InfoSolutions

Aascent InfoSolutions aspires to blend traditional expertise with cutting-edge technologies, enabling clients to excel in today’s competitive landscape with solutions that exceed expectations. We are seasoned software development company specializing in specific area, e.g., web applications, mobile apps, cloud solutions, Enterprise solutions, AI enabled solutions. With our immense experience in the IT industry, we have helped businesses like yours transform challenges into opportunities through innovative software solutions.

## 1.3 Executive Summary

The proposed solution is a secure, HIPAA-aware web-based application that integrates with PointClickCare to intelligently generate provider-specific rounding lists.

The system combines:

- Rule-based clinical logic

- Compliance-aware decisioning

- Future-ready AI capabilities

This platform will:

- Identify which patients need to be seen

- Explain why they are selected

- Provide compliance justification

- Improve operational efficiency for providers

The solution follows a phased approach (MVP → AI Enhancement) to deliver immediate value while enabling long-term innovation.

| Phase | Purpose | Fixed Fee | Timeline |
| --- | --- | --- | --- |
| Phase 0 | PCC Workflow Review — Technical Contribution |  | ~1 weeks from SOW execution |
| Phase 1 | Sandbox Validation & Logic Engine Prototype |  | 3 weeks from PCC sandbox access |
| Phase 2 | Build, Test & Deploy — Production V1 |  | 15 weeks from Phase 1 sign-off |

### 1.4 Objectives

- Improve Clinical Efficiency

- Ensure Regulatory Compliance

- Reduce Manual Workload

- Provide Explainable Decisions

- Enable AI-Driven Insights (future)

- Build Scalable & Secure Architecture

## 1.5 What We Are Building & Why

Medical Practice's physicians and nurse practitioners serve patients across multiple skilled nursing facilities. Every day, someone on the clinical team must review each patient's chart to determine whether a visit is required — checking for changes in vital signs, lab abnormalities, nursing note keywords, admission dates, payor requirements, and regulatory timelines. This manual process consumes significant staff time that could be redirected to direct patient care, introduces human error risk (particularly around regulatory compliance deadlines), and lacks any systematic mechanism to ensure that clinically significant changes are caught and acted upon in a timely manner.

The regulatory stakes are high. The system supports practice-defined compliance windows aligned with CMS guidance, requires that physicians see new skilled nursing admissions within 3 days and maintain at least a 30-day visit frequency. Nurse practitioners may perform interim visits but do not substitute for the physician's required regulatory encounter. A missed 30-day physician visit is not simply an administrative oversight — it is a compliance violation with potential survey, billing, and liability consequences.

# 2. Scope of Work

## 2.1 Project Scope Overview

This project involves the design, development, and deployment of a HIPAA-compliant Smart Rounding & Compliance Platform that integrates PointClickCare to automate patient selection for provider rounding.

Scope has been derived from the following documents shared by CoIPR Team with Aascent InfoSolutions:

- Smart_Rounding_Compliance_Platform_V1_MasterSpec_v1.7.docx received on 13-May-2026, this being the final version shared with Aascent Team

- PointClickCare API Documentation received on 25-APR-2026

The system will:

- Identify patients requiring visits

- Apply clinical and compliance rules

- Provide reasoning for selection

- Patient data display — name, facility, room, payor, status, last visit dates, days since admission, compliance badge

- Support secure provider access

- Lay the foundation for AI-driven enhancements

- Clinical AI flagging engine — abnormal vitals (fever, hypotension, hypertension, tachycardia, hypoxia, weight change), critical labs, nursing note keyword detection (fall, wound, AMS, hospital return, pressure ulcer, refusing meds, new O₂, and others)

- Per-provider rounding list generation: each of ~90 providers receive an individual role-filtered list each morning

- Clinical urgency flagging: abnormal vitals, PCC lab high/low flags, keyword detection in clinical notes, weight change (chronic and acute)

- Compliance rules engine: long-term (1 visit/month), short-term/rehab (3 visits/week); derived classification via two validated heuristics

- Same-day deduplication and physician-priority tiebreaker

- Carry-forward overflow: unseen patients promoted to next day at elevated priority; no hard cap on list size

- Admin numeric threshold editing (Level 1 editability only — no new rule types in V1)

- Multi-facility provider support

- Secure authentication: MFA, RBAC for Physician / NP / Admin roles

- HIPAA-compliant GCP deployment with encryption, audit logging, and BAA before any PHI access

- Training materials and full technical documentation

## 2.2 In-Scope Functional Components

### 1. User Authentication & Security

- Secure login system

- Multi-Factor Authentication (MFA)

- Keycloak Integration

- Role-based access control (Physician / NP / Admin)

- Session management & audit logs

### 2. Integration with EHR System

- Integration with PointClickCare APIs

- Data ingestion for:

  - Patient demographics

  - ADT records

  - Vitals

  - Diagnoses / conditions

  - Visit history

  - Facility and payer information

- Data synchronization (scheduled or near real-time)

### 3. Patient Data Management

- Centralized patient data storage

- Data normalization and validation

- Historical tracking for compliance logic

### 4. Rule-Based Decision Engine (Core MVP)

- Implementation of client-defined clinical rules

- Rule evaluation engine to:

  - Determine which patients should be seen

  - Assign priority levels (High / Medium / Low)

- Support for:

  - Time-based rules (e.g., last visit)

  - Condition-based rules

  - Admission/discharge triggers

### 5. Rounding List Generation

- Generate provider-specific lists:

  - Physician

  - Nurse Practitioner

- Facility-based filtering (based on schedule)

- Dynamic list updates

### 6. Decision Explanation & Compliance Visibility

- Display reason for selection per patient

- Show compliance logic (e.g., regulatory visit requirement)

- Transparent and auditable decision-making

### 7. User Interface (Web Application)

#### Key Screens:

#### Login & MFA screen

- Provider dashboard

- Rounding list view

- Patient detail view

- Admin panel (basic)

#### Features:

- Responsive design

- Search, filter, and sort capabilities

- Easy navigation for clinical users

### 8. Audit & Logging

### User activity tracking

- Rule execution logs

- Data access logs (HIPAA compliance)

### 9. Deployment & Hosting

- Cloud deployment (AWS / Azure)

- Secure environment configuration

- Backup & recovery setup

## 2.3 Out of Scope (Version 1)

- Direct modification of EHR(PCC) records

- Mobile application (unless specified)

- Integration with phone/message systems

- AI-based risk scoring or predictive prioritization (Phase 3)

- NLP / natural language processing for clinical notes (Phase 3)

- Custom rule editor or new rule type creation via UI (Phase 3)

- Billing, claims processing, or scheduling integration

- Higher-frequency sync / near real-time updates (Phase 3)

- Advanced BI reporting and analytics dashboards (Phase 3)

- Data migration from any legacy system

- Multi-language support, hardware procurement

## 2.4 Deliverables

- Fully functional web application

- Secure authentication system

- Integrated EHR data pipeline

- Rule-based rounding engine

- UI screens and dashboards

- Deployment setup (cloud)

- Technical documentation

- User training materials

# 3. System Requirements Specifications

### 3.1 Stakeholders

#### Operational Stakeholders

- Healthcare Administrators

- Clinical Supervisors

- IT Teams

#### End Users

- Physicians

- Nurse Practitioners

- Facility Staff (Admin)

# 4. Solution Overview

## 4.1 Overall Approach

We propose a modular, scalable architecture with:

- Secure integration with PointClickCare

- Rule-based decision engine

- AI augmentation (Phase 3+)

## 4.2 Key Features

### Core (MVP)

- Provider-specific rounding lists

- Rule-based patient selection

- Reason & compliance explanation

- Secure login (MFA)

### Advanced

- Rule configuration UI

- Analytics dashboard (Phase 3)

### AI (Future)

- Risk scoring

- Predictive prioritization

- NLP insights

# 5.0. Phase-wise Implementation Plan

CoIPR Software Consultants LLC owns the overall PCC Workflow Review submission under its existing engagement with the client. Aascent InfoSolutions contribute to the technical content under a small, standalone Phase 0 SOW billed directly to the client as a passthrough line item with no CoIPR markup. Phase 0 ends when PCC grants sandbox access.

The PCC Workflow Review is the critical path gate for all subsequent work. A technically complete and accurate submission for the first time eliminates the risk of rejection and rework delays. Aascent's architecture and integration expertise materially strengthens the submission by ensuring that every technical claim is verifiable and defensible

## 5.1   Phase-0 | PCC Workflow Review — Technical Contribution

### 5.1.1 Phase 0 Integration Data Flow Diagram

The diagram below illustrates the integration architecture that Aascent will document in the PCC Workflow Review submission, covering data flow, authentication model, and sync approach.

### 5.1.2 Phase 0 — Feature / Task Breakdown

| Feature / Task | Role | Hrs. |
| --- | --- | --- |
| [A] Technical Architecture Summary |  |  |
| Document high-level system component map: frontend (React SPA), backend (NestJS), rules engine, data adapter, GCP hosting layer | SA / Tech Lead | 2 |
| Describe each component's role, inter-component communication pattern, and API boundary | SA / Tech Lead | 1.5 |
| Define hosting model: GCP Cloud Run services, Cloud SQL (PostgreSQL), GCP VPC network topology | DevOps Engineer | 1.5 |
| Document security posture: TLS 1.2+ in transit, Cloud KMS at rest, audit log pipeline, MFA with OTP entry point | SA / Tech Lead | 2 |
| Produce architecture diagram suitable for PCC Workflow Review board (non-technical audience version) | SA / Tech Lead | 2 |
| Review and finalize architecture summary document against PCC Workflow Review formatting requirements | SA / Tech Lead | 1 |
| [B] Integration Approach Narrative | Role | Hrs. |
| Map end-to-end data flow: PCC API → data adapter → normalization layer → PostgreSQL → rules engine → provider list generation | Senior BE | 4 |
| Document PCC authentication model: API key management, OAuth token lifecycle, credential storage in GCP Secret Manager | Senior BE | 1 |
| Define sync model: scheduled daily pull architecture, job orchestration, retry/error handling, idempotency strategy | Senior BE | 1.5 |
| Document data fields ingested per sync cycle: demographics, ADT events, vitals, lab flags, clinical notes, visit history, facility data | Senior BE | 1.5 |
| Describe data normalization process: field name mapping, type coercion, null handling, duplicate detection | Senior BE | 1.5 |
| Define error notification and alerting model for failed sync cycles | Senior BE | 0.5 |
| Write integration narrative document formatted for inclusion in PCC Workflow Review submission | SA / Tech Lead | 1 |
| [C] Technical Review of CoIPR Draft Workflow Review Submission | Role | Hrs. |
| Review draft for technical accuracy: verify that described API usage, data fields, and integration patterns match planned approach | SA / Tech Lead | 1 |
| Verify all security and HIPAA-related claims in the draft | SA / Tech Lead | 0.5 |
| Check that authentication model described in Master Specification draft aligns with PCC Developer Program requirements | Senior BE | 0.5 |
| Identify any gaps or ambiguities that could trigger PCC review board questions or rejection | SA / Tech Lead | 0.5 |
| Deliver written feedback memo to Client with specific recommended edits and confirmations | SA / Tech Lead | 0.5 |
| [D] Optional — PCC Follow-up Call Support | Role | Hrs. |
| Prepare technical Q&A brief covering anticipated PCC reviewer questions on integration, security, and data handling | SA / Tech Lead | 0.5 |
| PHASE 0 TOTAL |  | ~25 hrs. |

Effort cap: 15–20 senior technical hours (SA / Tech Lead + Senior BE). The remaining hours are DevOps setup time. The total shown above represents a full task scope within the fixed fee.

### 5.1.3 Phase 0 — Effort Summary by Role

| Role | Phase 0 Hours | Fixed Fee Basis | Allocation |
| --- | --- | --- | --- |
| SA / Tech Lead | ~17 hrs. | Included | Fixed effort |
| Senior Backend Engineer | ~5 hrs. | Included | Fixed effort |
| DevOps / Cloud Engineer | ~3 hrs. | Included | Fixed effort |
| TOTAL | ~25 hrs. |  | Capped at 20 hrs. |

### 5.1.4 Phase 0 — Cost & Timeline

| Fixed Fee |  |
| --- | --- |
| Billing Model | Passthrough to the client. No CoIPR markup is applied. |
| Effort Cap | 20 senior technical hours (SA / Tech Lead + Senior BE) |
| Timeline | 1 week from Project Start |
| Phase Owner | CoIPR Software Consultants LLC (overall). Aascent InfoSolutions (technical content only). |
| Phase End Gate | PCC grants sandbox access |

## 5.2 PHASE 1   |   Sandbox Validation & Logic Engine Prototype

Phase 1 purpose: de-risk Phase 2 by validating that PCC actually exposes the data V1 depends on, before the client commits to the full build.

Every open item currently marked as 'pending sandbox validation' in the Master Specification v1.3 is resolved during Phase 1. The logic engine prototype running against live sandbox data is the primary validation vehicle — it proves that the rules can be implemented correctly before production development begins. Phase 1 ends with a signed completion document, a refined V1 specification, and a locked Phase 2 estimate with zero variance.

Phase 1 begins on PCC sandbox access being granted — not from contract signature.

### 5.2.1 Logic Engine Prototype Flow Diagram

The diagram below shows how the Phase 1 rules engine prototype processes sandbox data to produce per-provider patient lists for validation.

### 5.2.2 Phase 1 Deliverables (Locked)

The following deliverables are locked for Phase 1:

- Validated PCC data model assumptions against the live sandbox: All endpoint fields, data types, null rates, and availability confirmed against live sandbox — documented in the PCC Data Model Validation Report

- Confirmed field mappings for derived classifications: Long-term vs short-term heuristics, provider-patient assignment fields, and all clinical urgency signal fields confirmed and documented in the Field Mapping Document

- Working rules engine prototype running against sandbox data: All V1 rules implemented and validated against live sandbox patient records; output lists reviewed for correctness

- Refined V1 specification document reflecting any sandbox-driven adjustments: Master Specification updated with all confirmed field names, agreed defaults, and any scope adjustments surfaced by sandbox findings

- GCP technical fit confirmation: GCP Technical Fit Report confirming platform suitability for production deployment or flagging any constraint

- Locked Phase 2 estimate (no variance): Firm fixed fee and timeline for Phase 2 with all PCC uncertainty absorbed; no ranges

### 5.2.3 Phase 1 — Feature / Task Breakdown

| Feature / Task | Role | Hrs. | Note |
| --- | --- | --- | --- |
| [A] Validated PCC Data Model -- All Endpoints |  |  |  |
| Set up GCP sandbox → PCC Developer sandbox connectivity; confirm token lifecycle | DevOps | 6 |  |
| Authenticate + validate all 7 PCC endpoints (demographics, ADT, vitals, labs, notes, visit history, facilities) | Senior BE | 32 |  |
| Document all field names, formats, null rates; produce PCC Data Model Validation Report | SA / TL | 7 |  |
| [B] Confirmed Field Mappings -- All Derived Classifications |  |  |  |
| Map provider-patient assignment fields (Physician + NP) | Senior BE | 12 |  |
| Map LT vs ST/Rehab classification heuristics (LOS, PT frequency, edge cases + default behavior) | Senior BE | 8 |  |
| Map all clinical urgency signal fields (vitals, labs, keywords, weight change) | Senior BE | 12 |  |
| Produce Field Mapping Document; propose default for ambiguous classification cases | SA / TL | 5 |  |
| [C] UI Wireframe Designs |  |  |  |
| Design wireframes + screen layouts for all V1 screens (dashboard, rounding list, admin panel) | Frontend | 32 |  |
| [D] Refined Spec + GCP Fit Report + Locked Phase 2 Estimate |  |  |  |
| Update Master Specification v1.3 with all confirmed field names, defaults, and sandbox findings | SA / TL | 6 |  |
| Produce GCP Technical Fit Report confirming production suitability or flagging constraints | DevOps | 4 |  |
| Produce locked Phase 2 estimate (zero variance); present to Client for review before client submission | SA / TL | 5 |  |
| PHASE 1 TOTAL | 129 hrs |  |  |

### 5.2.4 Phase 1 — Effort Summary by Role

| Role | Hours | Allocation | Primary Focus |
| --- | --- | --- | --- |
| SA / Tech Lead + PM | 23 hrs | 100% | Architecture, field mapping docs, rules engine oversight, Phase 2 estimate, |
| Senior Backend Engineer | 64 hrs | 100% | PCC sandbox validation, field mappings |
| Frontend Engineer | 32 hrs | 100% | Wireframe designs, login screens, prototype, provider screen, Admin screen |
| DevOps / Cloud Engineer | 10 hrs | 100% | GCP sandbox + production infra, CI/CD pipeline analysis, GCP Infrastructure |
| TOTAL | 129 hrs | -- | -- |

### 5.2.5 Phase 1 — Cost & Timeline

| Fixed Fee |  |
| --- | --- |
| Timeline | 3 weeks from PCC sandbox access being granted |
| Start Trigger | PCC sandbox access granted (not contract signature) |
| Owner | Aascent InfoSolutions (technical). CoIPR Software Consultants LLC (PM, client communications, QA oversight). |
| Phase End Gate | Phase 1 sign-off document executed by both parties. Locked Phase 2 estimate issued. |

## 5.3 PHASE 2   |   Build, Test & Deploy — Production V1

Phase 2 delivers a production-ready V1 application as scoped in the Master Specification, full HIPAA-compliant deployment, training materials, and technical documentation. It begins upon Phase 1 sign-off.

All PCC data assumptions are confirmed, and all field mappings are locked before a single line of production code is written.

Phase 2 is organized into four 2-week sprints. Each sprint has a clear milestone gate, and a defined set of deliverables that can be reviewed before the next sprint begins.

### 5.3.1 System Architecture Diagram

The diagram below shows the full production architecture that Phase 2 will build and deploy.

### 5.3.2 Phase 2 Deliverables (Locked)

- Production-ready V1 application: Fully functional web application per the refined Master Specification; all rules, all screens, all roles

- Full HIPAA-compliant deployment: GCP deployment within client's existing GCP organization, encryption at rest and in transit, BAA countersigned before PHI ingestion, audit logging complete

- Training materials: Provider Quick-Start Guide, Admin User Guide, IT Deployment Runbook

- Technical documentation: Architecture Decision Records, API Reference (OpenAPI), system architecture document, database schema documentation

### 5.3.3 Phase 2 — Feature / Task Breakdown

| Feature / Task | Role | Hrs | Note |
| --- | --- | --- | --- |
| [A] PCC Integration -- Production Hardening (sandbox code promoted to production) |  |  |  |
| Build PCC API client (production): credential loading from Secret Manager, HTTP client, timeout/retry config | Senior BE | 6 | Not a rebuild |
| Implement OAuth token acquisition + refresh for production PCC endpoint | Senior BE | 4 |  |
| Promote all 7 ingestion pipelines from sandbox to production (endpoint swap + Secret Manager creds) | Senior BE | 4 | Not a rebuild |
| Implement incremental sync: only pull records changed since last sync to reduce API load | Senior BE | 4 |  |
| Implement sync error handling: dead-letter queue, exponential backoff, error notification model | Senior BE | 4 |  |
| Implement sync status tracking: log each run's start/end/records processed/errors | Senior BE | 2 |  |
| Build integration test suite validating all pipelines against production PCC data | QA | 10 |  |
| [B] Rules Engine -- Production Build (on sandbox data, production-quality code) |  |  |  |
| Design rules engine architecture: input model, evaluator pipeline, output model, rule audit log interface | SA / TL | 4 |  |
| Implement per-provider list generation (filter by role + facility + assigned patients) | Senior BE | 10 |  |
| Implement LT vs ST/Rehab classification + confirmed default behavior | Senior BE | 10 |  |
| Implement compliance timing rules -- 30-day (LT) and 3×/week (ST/Rehab) | Senior BE | 6 |  |
| Implement abnormal vitals evaluator (all locked thresholds) | Senior BE | 4 |  |
| Implement lab abnormal flag evaluator (PCC H/L/HH/LL indicators) | Senior BE | 8 |  |
| Implement keyword detection engine (11-keyword list, all confirmed PCC note types) | Senior BE | 16 |  |
| Implement chronic + acute weight change evaluators | Senior BE | 8 |  |
| Implement physician-priority tiebreaker, carry-forward overflow, same-day deduplication | Senior BE | 10 |  |
| Implement multi-facility provider support + clinical urgency priority scoring | Senior BE | 10 |  |
| Implement compliance timing as secondary sort | Senior BE | 6 |  |
| Build rule execution audit log (which rules fired per patient per run) | Senior BE | 6 |  |
| Build rules engine unit test suite (all evaluators -- positive, negative, edge cases) | QA | 8 |  |
| Validate prototype output against live sandbox clinical scenarios | QA | 8 |  |
| Document prototype findings, rule adjustments, and edge cases | SA / TL | 4 |  |
| [C] GCP Production Infrastructure + CI/CD |  |  |  |
| Provision production GCP project, IAM roles, service accounts within client GCP org | DevOps | 10 |  |
| Provision Cloud Run (API + rules engine worker), Cloud SQL (PostgreSQL), Memorystore (Redis) -- production-grade | DevOps | 8 |  |
| Configure Cloud, Secret Manager, VPC private connectivity, Cloud Logging + Monitoring | DevOps | 6 |  |
| Build CI/CD pipeline: GitHub Actions → GCP Cloud Build → Cloud Run; automated test gates | DevOps | 12 |  |
| Define + deploy production database schema; implement Flyway/Liquibase migration framework | Senior BE | 12 |  |
| Define API project structure, NestJS module boundaries, folder layout, coding standards | SA / TL | 6 |  |
| [D] production OAuth2 integration |  |  |  |
| Implement OAuth2 + MFA Keycloak Implementation, MFA | Senior BE | 8 |  |
| Implement JWT issuance, validation, refresh, revocation, idle session timeout | Senior BE | 8 |  |
| Implement RBAC: define Physician / NP / Admin permission sets; enforce on all API endpoints | Senior BE | 10 |  |
| Implement audit logging middleware: user identity, action, timestamp, IP on every API call | Senior BE | 10 |  |
| Implement data access logs: every PHI field read logged with patient ID + data category | Senior BE | 10 |  |
| Build login screen MFA entry screen in React SPA | Frontend | 20 |  |
| Configure TLS 1.2+ enforcement on all Cloud Run services and Cloud SQL connections | DevOps | 4 |  |
| Conduct OWASP scan on auth endpoints; remediate findings | QA | 4 |  |
| [E] API Layer -- All Endpoints (new in Phase 2) |  |  |  |
| Build Provider Dashboard API: aggregate stats per logged-in provider (total patients, high-priority count, compliance status) | Senior BE | 4 |  |
| Build Rounding List API: per-provider patient list with priority, urgency flags, compliance status, and reason fields | Senior BE | 4 |  |
| Build Patient Detail API: full patient clinical summary, active rule trigger explanations, compliance breakdown | Senior BE | 4 |  |
| Build Admin Threshold Edit API: validate + persist + log numeric threshold changes | Senior BE | 4 |  |
| Build Admin User Management API: create/read/update users, assign and change roles | Senior BE | 4 |  |
| Build Manual Sync Trigger API + Audit Log Export API (paginated, filterable by date/user/event) | Senior BE | 5 |  |
| Apply RBAC enforcement on all API endpoints (inherits Phase 1 RBAC layer) | Senior BE | 3 |  |
| Write OpenAPI / Swagger documentation for all API endpoints | Senior BE | 4 |  |
| Build API integration test suite for all endpoints | QA | 8 |  |
| [F] HIPAA Security Hardening & Compliance Review |  |  |  |
| Conduct OWASP ZAP DAST full scan on production application; document and remediate all High + Medium findings | QA | 8 |  |
| Conduct RBAC penetration test: attempt cross-role data access for each role combination; document and fix | QA | 6 |  |
| Validate audit log completeness: every PHI access event captured with required fields (user, action, patient ID, timestamp, IP) | Senior BE | 4 |  |
| Validate encryption at rest (Cloud SQL + Cloud Storage) + verify KMS key rotation policy | DevOps | 3 |  |
| Conduct HIPAA Security Rule technical safeguards review against all implemented controls | SA / TL | 4 |  |
| Prepare BAA compliance attestation document for client countersignature before PHI access begins | SA / TL | 2 |  |
| [G] QA -- Final Testing & Regression |  |  |  |
| Write comprehensive test plan mapping all V1 functional requirements to Master Specification sections | QA | 8 |  |
| Execute integration test suite across all modules (auth, PCC pipeline, rules engine, API layer, UI) | QA | 12 |  |
| Build + execute Playwright E2E test suite covering all primary user flows for Physician, NP, and Admin roles | QA | 16 |  |
| Execute regression test suite after each bug-fix cycle | QA | 8 |  |
| Coordinate + support client UAT sessions; capture and triage reported issues | SA / TL | 8 |  |
| Resolve all UAT-identified defects; re-test and obtain client sign-off | Senior BE | 8 |  |
| Project management: sprint planning, risk register, status reports, change management (all of Phase 2) | PM | 28 |  |
| [H] Deployment & Go-Live |  |  |  |
| Promote application from Phase 1 production environment to live; configure autoscaling, health checks, traffic routing | DevOps | 8 |  |
| Configure production monitoring dashboards and alerting thresholds in GCP Cloud Monitoring | DevOps | 3 |  |
| Execute production smoke test: validate all services live, PCC sync completing, lists generating correctly | QA | 4 |  |
| Conduct performance test: simulate peak load of ~90 concurrent provider logins and list refreshes | QA | 4 |  |
| Confirm BAA countersigned by client before enabling PHI data ingestion | SA / TL | 1 |  |
| [I] Training Materials & Technical Documentation |  |  |  |
| Write Provider Quick-Start Guide (login, list view, priority indicators, compliance explanations) | SA / TL | 4 |  |
| Write Admin User Guide (threshold editing, user management, sync monitoring, audit log access) | SA / TL | 4 |  |
| Write IT Deployment Runbook (GCP environment, CI/CD, secret rotation, backup/recovery procedures) | DevOps | 3 |  |
| Write Technical Architecture Document + API Reference Documentation (from OpenAPI spec) | SA / TL | 5 |  |
| [J] UI Patient/NP Login Screen |  |  |  |
| Build Provider Dashboard screen: stats widget, compliance status, navigation to rounding list | Frontend | 14 |  |
| Build Rounding List screen: tabular view with name, facility, room, priority indicator, compliance badge, last visit, days since admission, reason | Frontend | 14 |  |
| Implement sorting + filtering + search on Rounding List (by priority, compliance urgency, facility, last visit, patient name/room) | Frontend | 18 |  |
| Build Patient Detail screen: demographics, diagnosis, vitals, lab flags, note keyword hits, visit history, compliance explanation | Frontend | 16 |  |
| Implement compliance explanation component + carry-forward badge + WCAG 2.1 AA | Frontend | 12 |  |
| UI unit tests + cross-browser testing (Chrome, Firefox, Safari, Edge) | QA | 6 |  |
| [K] UI -- Admin Screens |  |  |  |
| Build Admin Threshold Editor screen: list all editable numeric thresholds, edit fields, save controls, before/after confirmation dialog | Frontend | 12 |  |
| Build Admin User Management screen: list users, assign/change roles, activate/deactivate accounts | Frontend | 8 |  |
| Build Admin Audit Log screen: paginated log viewer with date/user/event type filter and CSV export | Frontend | 6 |  |
| Build Admin Sync Status screen: last run timestamp, records processed, errors, manual refresh button | Frontend | 10 |  |
| PHASE 2 TOTAL | 587 hrs |  |  |

### 5.3.4 Phase 2 — Effort Summary by Role

| Role | Hours | Allocation | Primary Focus |
| --- | --- | --- | --- |
| SA / Tech Lead + PM | 42 hrs | 100% | Architecture governance, HIPAA review, BAA coordination, UAT facilitation, docs, sprint oversight Sprint planning, risk register, weekly status reports, change management -- explicit in Phase 2 |
| Senior Backend Engineer | 220 hrs | 100% | PCC production hardening, full API layer, rules engine (production build), Auth/RBAC, Keycloak Implementation, DB schema, HIPAA audit log validation, UAT defect resolution, |
| QA Engineer | 110 hrs | 100% | Integration tests, E2E, OWASP RBAC pen test, regression, UAT support, go-live smoke test |
| DevOps / Cloud Engineer | 57 hrs | 25% | Go-live environment promotion, autoscaling config, monitoring dashboards, deployment runbook |
| Frontend | 130 hrs | 100% | PCC actual API integration and match with wireframes |
| PM | 28 hrs | 100% | Project Management and task allocations |
| TOTAL | 587 hrs | -- | -- |

### 5.3.5 Phase 2 — Cost & Timeline

| Fixed Fee |  |
| --- | --- |
| Timeline | 15 weeks from Phase 1 sign-off |
| Start Condition | Phase 1 sign-off document executed by both parties |
| Owner | Aascent InfoSolutions (technical execution). CoIPR Software Consultants LLC (PM, client comms, change management, QA oversight, HIPAA/BAA coordination). |
| BAA Requirement | BAA countersigned by client before production PHI ingestion begins |

# 6.0 Sample UI Screens

## 6.1. Login Screen

- Email login

- Password

- MFA code

- “Remember me”

## 6.2. Rounding List Screen

- Patient Name

- Room

- Priority (High/Medium/Low)

- Reason

## 6.3. Admin Rule Management

- Rule name

- Condition

- Priority

- Status (Active/Inactive)

### 6.4 Why our team is a fit

- Healthcare-Focused AI Expertise: We have strong experience in developing AI-driven solutions, particularly in computer vision and mobile-based applications, enabling us to deliver accurate and reliable clinical insights.

- Phased Implementation Expertise: We prioritize delivering a functional MVP quickly to provide immediate value, while designing the system architecture to support scalable enhancements such as advanced AI models and optional integrations.

- Data Security & Privacy Awareness: We follow best practices for secure data handling, including on-device encryption and controlled access, ensuring patient data remains protected.

- Proven Delivery Capability: Our team has successfully delivered complex mobile and AI-based applications, demonstrating our ability to manage end-to-end development—from model training to deployment and user experience design.

## 6.5 Proposed Technology Stack

The following stack is confirmed for all phases of this engagement. This replaces the technology section of the original proposal and addresses the client's request for stack confirmation.

| Layer | Technology / Detail |
| --- | --- |
| Frontend | React (with Next.js routing). |
| Backend | Node.js with NestJS framework. |
| Database | PostgreSQL on GCP Cloud SQL (primary data store). |
| Authentication | OAuth 2.0 / SAML 2.0. |
| Cloud | Google Cloud Platform (GCP) — deploying into client's existing GCP organization with HIPAA BAA in place. Cloud-agnostic architecture where feasible. |
| Infrastructure | GCP Cloud Run (containerized services). Other Service to be discuss once we have call. |
| Observability | Cloud Monitoring, alerting policies. Structured audit log for all PHI access events. |
| Security | OWASP scanning. TLS 1.2+ enforcement. RBAC on all endpoints. Audit logging middleware on all API routes. |
| AI / ML | Not in V1 scope. All AI features (risk scoring, NLP, predictive prioritization) are deferred to Phase 3–4. |

## 6.6 Questions & Assumptions

Assumptions:

- Data from PointClickCare is:

- Accurate

- Complete

- Timely

- Required fields are available:

- Last visit date

- Diagnosis

- Vitals

- API access to PointClickCare will be granted

- Need set of rules for visit criteria

- Integration is technically feasible

- No strict rate limits blocking system

- Client's existing GCP infrastructure and Google HIPAA BAA remain in place through the project lifecycle

- Client will confirm the acute weight change threshold before Phase 2 logic engine build begins

- CoIPR Software Consultants LLC will facilitate client feedback and approvals within 5 business days of each review request

- No strict PCC API rate limits that would prevent the daily scheduled sync from completing within the sync window

- MFA SMS/Email notifications are billed separately as a usage-based operational expense and are not included in the implementation cost estimate (Approx. $0.0075–$0.05 per SMS depending on country/carrier).

# 7.0. Team Structure

| Role | Name | Primary Responsibilities | Allocation |
| --- | --- | --- | --- |
| SA / Tech Lead + PM | Indra Gohil | Architecture, HIPAA oversight, code review, client comms, sprint planning, risk management, UAT coordination | 100% |
| Senior Backend Engineer | Alpesh Parmar | Node.js/NestJS API, PCC integration adapter, logic/rules engine, compliance engine, database design and migrations, GCP deployment support | 100% |
| Backend Engineer | Ankur Sureja | API endpoints, RBAC enforcement, audit logging, admin threshold management API, unit test authorship | 100% |
| Frontend Engineer | Jigar Nakum | React SPA, auth flow, per-provider list views, admin dashboard | 100% |
| QA Engineer | Ashok Mamnani | Test plans, integration tests, E2E tests, OWASP scan, UAT support, regression suite | 75% |
| DevOps / Cloud Engineer | Alpesh Parmar | GCP Infrastructure | 50% |

# 8. Aascent Confirmations

The revisions reflect a deeper alignment with business requirements, technical expectations, and operational workflows discussed during the review process. Key enhancements include scope adjustments, additional feature definitions, improved system design considerations, and refined effort estimations.

These updates ensure that the proposal accurately captures the intended functionality, compliance requirements, and performance expectations, while minimizing ambiguities and implementation risks.

## 8.1 GCP Capability

Aascent InfoSolutions confirms GCP capability across all services required for this engagement: Cloud Run, Cloud SQL, Cloud KMS, Secret Manager, Memorystore, Cloud Build, Cloud Monitoring, and GCP IAM. Our SA/Tech Lead and DevOps Engineer have delivered production GCP deployments and are equipped to work within the client's existing GCP organization. We anticipate no technical constraint requiring an alternative cloud provider. Final confirmation is documented in the Phase 1 GCP Technical Fit Report.

## 8.2 HIPAA BAA

Aascent InfoSolutions confirms it will execute a Business Associate Agreement with the client before any PHI or real patient data is accessed. During Phase 1 sandbox work, only synthetic or de-identified data will be used until the BAA is countersigned. Aascent will flow equivalent BAA terms to any subcontractors or vendors with PHI access.

## 8.3 Backend Framework

The production backend is confirmed as Node.js with the NestJS framework. The Spring Boot reference in Section 9.0 of the original proposal was carried in from a prior template in error. It has been removed from this version. All backend work across Phase 1 and Phase 2 are delivered in Node.js / NestJS.

## 8.4 Phase Timeline Trigger

Phase 1 and Phase 2 build timelines run from PCC sandbox access being granted — not from contract signature. PCC's Workflow Review period is outside the control of either party and does not count against Aascent's delivery clock.

## 8.5 PM Model

CoIPR Software Consultants LLC acts as project manager across all phases, owning client communications, change management, QA oversight, and regulatory coordination (BAA, HIPAA, PCC). Aascent InfoSolutions owns technical execution and all technical deliverables. CoIPR's PM fee is a separate line item from Aascent's Phase 1 and Phase 2 numbers. Phase 0 is a passthrough with no CoIPR markup.

# 9. Agreement Terms

- Upon Acceptance of this Proposal, Aascent InfoSolutions Will initiate the process of team deployment to start this project. Within 3 days of signing this proposal, Aascent InfoSolutions will send a start date of the project.

- Change Management Overview: For a SOW to be modified, a Project Change Request (“PCR”) must be executed in writing by a duly authorized representative of each Party.  Each PCR will describe the proposed change, the rationale for the change, and the expected effects, if any, the change will have on Project cost, schedule, and other subjects. Upon Acceptance by ColPR will be taken up for execution/implementation.

# 10. Acceptance

| For, Aascent InfoSolutions | For, CoIPR Team |
| --- | --- |